## Backlog
id | theme | as a/an | I want to… | so that… | notes | acceptance criteria | added in sprint | story points
1 | Admin | User | Display rendered graphics in a user friendly window | we can create shapes and output them appropriately |  | A working canvas and supporting rendered shapes | 1 | 100 | As a user, all graphic objects (i.e. shapes including text) should be displayed in a very user friendly window.
2 | Admin | User | Produce a shape listing sorted by shape perimeter and ID | perimter and ID will sort shapes properly |  | Verify that sorting algorithm sorts shapes by perimeter | 2 | 50 | As a user, I can produce a shape listing report of ONLY shapes with a perimeter sorted by perimeter (at any time) that will include shape type, ID, and perimeter.
3 | Content | User | Keep track of my history | I can revert something if it is not desired |  | Verify changes made to the program were recoreded | 2 | 20 | As an user, I can see the History of tasks that have been done.
4 | Content | Admin | Add, move, and remove shapes | They may be manipulated and changed to provide functionality |  | Verify the shapes can be manipulated | 2 | 10 | As an administrator, I can move, add, and remove shapes, including text, that will be visible in the rendering area.
5 | Admin | Programmer | Keeps track of rendered shapes | Each shape will have a specific ID |  | Verify that each shape has a specific ID and is rendered properly | 2 | 100 | As a programmer, it is necessary to use a shapefile that will keep track of all shapes being rendered and all shapes should have a unique ID.
6 | Content | User | List company contact info with logo | The company may be contacted for further ventures |  | Verify Logo & name matches the company | 1 | 20 | As a user, I need to be able to contact the company through the logo and/or name.
7 | Admin | Admin | Changes made will be saved between executions | User won't have to worry about losing unsaved work |  | Verify the changes were saved | 1 | 30 | As an Admin, all the changes I have made should be saved between executions.
8 | Content | Programmer | Create a canvas interface | We can see a coordinate plane of the shapes |  | Verify that shapes are assigned to correct coordinates on the grid | 1 | 20 | As a programmer, it is necessary that the graphic window be dimensions of 1000 pixels by 500 pixels with an easy to understand coordinate system.
9 | Admin | User | Sort a shape listing report | Establish a listing report |  | Verify sorting algorithm and printed listing report works | 2 | 20 | As a user, I can produce a shape listing report that can sort by shape ID (at any time) that will include all shape properties.
10 | Admin | User/Admin | Login for program and sort shapes based on area | Admins can login to program and output a listing based on area | Modified to add login to backlog | Verify login works and output matches areas of shapes | 2 | 30 | As a user, I can produce a shape listing report of ONLY shapes with an area sorted by area (at any time) that will include shape type, ID, and area.

## Done
id | theme | as a/an | I want to… | so that… | notes | acceptance criteria | added in sprint | closed in sprint | story points
1 | Content | User | view a home page | I can see the most important content at a glance and quickly understand the site navigation |  | Verify shape is added to the vector | 1 | 1 | 20
2 | Personalisation | User | be able to log in to the site | I can see tailored content and manage my relationship with the company |  | Verify syntax errors result in accurate detailed errors | 1 | 1 | 20
3 | Personalisation | User | be able to register for an account | I can login and gain all the benefits of being an authenticated user |  | Verify username and passwords work | 1 | 1 | 10
4 | Content | Admin | Add a selection sort to sort the shapes | The shapes will be sorted by their respective ID's and content | Added for extra credit | Verify that the selection sort works properly within the canvas | 2 | 2 | 20

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
0 | 400 | 0 | 0 | 0% | 0 | 400
1 | 230 | 170 | 0 | 43% | 0 | 230
2 | 110 | 400 | 110 | 78% | -110 | 0
3 | 70 | 470 | 140 | 87% | -140 | -70

## Lists
0
5
10
20
30
50
100
150
200
400
1000