## Sprint1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Sprint Review
As a user, all graphic objects (i.e. shapes including text) should be displayed in a very user friendly window. | Task 1 | Jeff, Taylor | Done | 3 | 1.5 | 2.5 | 1 | 0 | 0
| Task 2 | Jeff, Taylor | In Progress | 2 | 0 | 1.5 | 0 | 1 | 1
As a programmer, it is necessary that the graphic window be dimensions of 1000 pixels by 500 pixels with an easy to understand coordinate system. | Task 1 | Jeff, Oscar | Done | 4 | 1 | 2 | 1 | 0 | 0
| Task 2 | Jeff, Isaac | Done | 3 | 1 | 1 | 2 | 0 | 0
| Task 3 | Jeff, Oscar, Isaac | In Progress | 2 | 2 | 0 | 0 | 0 | 2
As an Admin, all the changes I have made should be saved between executions. | Task 1 | Oscar, Caroline | Done | 2 | 0 | 0 | 0 | 1 | 0
| Task 2 | Caroline | Done | 3 | 1 | 1 | 1 | 1 | 0
As a user, I need to be able to contact the company through the logo and/or name. | Task 1 | Oscar, Taylor | Done | 1 | 1 | 0 | 0 | 2 | 0
| Task 2 | Oscar, Taylor | Done | 1 | 0 | 0 | 0 | 0 | 0
| Task 3 | Oscar, Taylor | Done | 1 | 1 | 0 | 0 | 0 | 0
| Total |  |  | 22 | 8.5 | 8 | 5 | 5 | 3
Sprint Goal
Goal - Create the framework for a working user interface, Code in admin privledges, Complete company info/logo, & work on graphic window for shape objects