## Sprint2
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Sprint Review
As a user, I can produce a shape listing report of ONLY shapes with a perimeter sorted by perimeter (at any time) that will include shape type, ID, and perimeter. | Task 1 | Taylor | Done | 3 | 1 | 1 | 0 | 1 | 0
| Task 2 | Taylor | Done | 2 | 1 | 1 | 0 | 1 | 0
As an user, I can see the History of tasks that have been done. | Task 1 | Caroline | Done | 3 | 1 | 0 | 1 | 0 | 0
| Task 2 | Jeff | Done | 2 | 0 | 1 | 0 | 1 | 1
| Task 3 | Jeff | Done | 2 | 0 | 0 | 1 | 1 | 0
As an administrator, I can move, add, and remove shapes, including text, that will be visible in the rendering area. | Task 1 | Travis | Done | 3 | 1 | 0 | 1 | 0 | 0
| Task 2 | Oscar | Done | 4 | 1 | 1 | 1 | 1 | 1
| Task 3 | Isaac | Done | 3 | 1 | 1 | 0 | 0 | 1
As a programmer, it is necessary to use a shapefile that will keep track of all shapes being rendered and all shapes should have a unique ID. | Task 1 | Travis, Isaac | Done | 3 | 1 | 2 | 0 | 0 | 0
As a user, I can produce a shape listing report that can sort by shape ID (at any time) that will include all shape properties. | Task 1 | Travis | Done | 2 | 1 | 0 | 1 | 0 | 0
| Task 2 | Isaac | Done | 2 | 0 | 1 | 1 | 0 | 1
As a user, I can produce a shape listing report of ONLY shapes with an area sorted by area (at any time) that will include shape type, ID, and area. | Task 1 | Travis, Jeff | Done | 3 | 1 | 0 | 2 | 1 | 0
| Task 2 | Travis | Done | 4 | 0 | 0 | 2 | 2 | 0
| Task 3 | Travis, Isaac | Done | 2 | 0 | 0 | 0 | 2
| Total |  |  | 38 | 9 | 8 | 10 | 10 | 4
Sprint Goal
Goal - Finish implementing the user canvas, Organize all source code related to shapes, implement a working selection sort, finish working on the read and write to the shape.txt file, produce any other agile documentation, run valgrind, and run deoxygen